## Daily_Log
Date | Doubt And Important Work with Next Day's Task (NT) | Week | Day to Day Work Update and Progress in Details (inc - incomplete)
2024-01-08 | Introduction to ECL IDE | Week 1 | Office Laptop Set up with Teams and Outlook with training videos on Phishing and Safety
2024-01-09 | NT: Start with Introduction Level 1 | Week 1 | Started on with HPCC Architecture and its different componets and accessed myworkday and other tools
2024-01-10 | same as above | Week 1 | Started off with Introduction to ECL Level 1 Training did till lesson 5 Spraying
2024-01-11 | same as above | Week 1 | Then did till lesson 14 which was RECORD and DATASET
2024-01-12 | same as above | Week 1 | Then did till lesson 20 which is SET definitions
2024-01-15 | Introduction to ECL Level 1 | Week 2 | Till Lesson number 24 was done, which is VALUE Definition
2024-01-16 | same as above | Week 2 | Till Lesson number 28 (Last Lesson) was done which is OUTPUT and DESPRAY
2024-01-17 | Introduction to ECL Level 2 | Week 2 | Did till Lesson 6a: Data Evaluation DISTRIBUTE and INLINE , found out Azure Data Lake Analytics will retire end Febuary
2024-01-18 | same as above | Week 2 | Did till Lesson 8: ITERATE SERVICE, READ about Azure Synapse
2024-01-19 | same as above | Week 2 | Did till the END which is Lesson 11: JOIN Part 1 and Part 2
2024-01-22 | NT: Azure AZ 900 | Week 3 | Started off with Azure AZ 900 course and started a doc on Comparing all 4 stated Technologies (inc)
2024-01-23 | continued on with AZ 900 | Week 3 | Had a call with Sathish, understood about the use of Ansible and Terraform and some clarity on flow of data in project
2024-01-24 | Made the 4 Technologies Doc (OLAP, GitPod, Open BI, Azure Synapse ) | Week 3 | Read about Terraform and Ansible and did more of AZ 900, I also saw a Tutorial on YouTube on the use of Terraform
2024-01-25 | Which Part of Synapse needs to be Integrated? | Week 3 | Finished the 4 Tech document, read about SpaceLift, which is CI/CD option for IAC (eg. Terraform, Ansible) saw a tutorial on same
2024-01-29 | Final Project Deliverable and Project Timeline? | Week 4 | Had a call with Srini, unsure of the exact deliverables and hence working on Azure for now, rest on hold
2024-01-30 | NT: Work on 4 Tech's final doc and finish the Azure Synapse course | Week 4 | Finished AZ 900, read about Azure ARM ,since rest on hold, working on Azure Synapse tutorials and (inc: 4 Tech final document)
2024-01-31 | NT: same as above, work on PTT for Hugo, also where to deploy the system? | Week 4 | Started Azure Synpase course in details, tried working on it, but needs personal account set-up, internship project link is down
2024-02-01 | Continue on with Synapse and then start off with Implimentation | Week 4 | Worked on PTT for Hugo, finished the 4 Tech Document, Read and did a Tutorial on Microsoft Azure Synapse Analytics
2024-02-02 | NT: Start off with Implimentation once the project timeline is final | Week 4 | Continued on with Azure Synapse, read on Terraform and Ansible and then some Docker as that might be the road map, start imp
2024-02-05 | NT: Install HPCC Locally then do Azure Synapse hands on experience, arya chat password rem | Week 5 | Had a call with Srini and Sathish, for now got to Install HPCC into my personal machine with steps on training portal and take admin
2024-02-06 | same as above, also make a Block Diagram for flow eg Dali server install etc | Week 5 | Just set up the env for defining the project, waiting for the Local Admin Access, and checking the Azure Synapse with mini project
2024-02-07 | Not setup plugins or tools, just bare metal platform, on step: 1 and page: 10 | Week 5 | Started off with the setup of HPCC in single node, got file with wget with Sathish's help, reading doc Install on ROOT , startup
2024-02-08 | done dependency job for hpccsystems-platform.target failed. See 'journalctl -xe' | Week 5 | Was able to complete and configure the HPCC Cluster on my Local Machine, with setting up of ECL IDE, ECL Watch, no plugin / tools
2024-02-09 | Find ways in which we need to connect other PC's to my Instanace HPCC via intra | Week 5 | Had a word with all, for finalizing Azure, and then we need to impliment that, mean time read Open BI, see Hugo mail, personal ac
2024-02-12 | NT: Work on IP config for Windows and Linux Machine to one so to ping together B82 | Week 6 | Finalized on Azure First with RELX account 30 days, working on the testing of HPCC Instance to IntraNet, time out on Linux IP issue
2024-02-13 | NT: Work on Integration of simple Power BI using Jessie's Method on links | Week 6 | Due to Security concerns Azure is on hold, working on Power BI Integration, that method is not sure, see notepad for links
2024-02-14 | NT: Try working in the WsSQL Direction try with SQL Server First then on HPCC | Week 6 | Worked on Lee's Method for Integration as it's more automated and latest, using REST URL by putting data on WorkUnit then ESP
2024-02-15 | NT: See how to integrate Power BI with WsSQL via connection link / env jar file loc | Week 6 | Started off with set up and done of WsSQL on my Local HPCC, Installed JDBC's JAR file, now Power BI data other, see for ODBC connection
2024-02-16 | NT: Need Connection String/Link for even LocalHost of WsSQL via ODBC where Install | Week 6 | Installed JAR in WSL, can't find ODBC for HPCC, Installed Postman for API call to Localhost WsSQL to see if data in ECL Watch, need con l
2024-02-19 | NT: No ODBC, do SOAP API on WSDL and see Zappy and SOAP UI, do from Web , YT , Web Service | Week 7 | Looked at Tech Talk 10 Rodrigo who made WsSQL (talk on Web Service creation) on Dynamic ESDL, working on SOAP API in PowerBI, Web
2024-02-20 | NT: Did the SOAP API with w3, some Parameter issues, work on SOAP API for HPCC Systems also | Week 7 | Had a call with Xiaoming and got clarity, any doubts reach Rodrigo, did the w3schools SOAP API Test, now need to try with HPCC Systems to WsSQL
2024-02-21 | NT: Work on final integration of Power BI using the WSDL and SOAP call in Blank Query | Week 7 | Had a look at WSDL and ESDL, I will need to make a WSDL then I can write the SOAP call in the Advance Editor in Power BI, then establish connection
2024-02-22 | Done: Was able to send request from SOAP UI to WsSQL, now try the same for Power BI | Week 7 | Had a call with Srini and took help from Nirmal and will look into testing or sending the Request for WsSQL from SOAP UI, then can work on the same at Power BI
2024-02-23 | Done above, now waiting from the next deliverable to work on, now get OUTPUT ON POWER BI | Week 7 | Was able to establish a connection from Power BI to WsSQL and that to HPCC, so fine tuning and some sample data will be done next but so far deliv done
2024-02-26 | NT: Solve error on Data as Table / using XML.Table() Function, Encoding failed on WsSQL End also | Week 8 | Tried working on the getting data as Tables/Rows on Power BI, but error on "Type based on Record/List" and also even WsSQL output is incorrect XML.Table()
2024-02-27 | NT: Same as above, we need to solve the SOAP Response Encoding problem as that will solve .Table() | Week 8 | Had a call with Srini, and the issue is the Encoding as in the WsSQL output the answer in the SOAP Response is also not correct XML, so anyway in the scrpt
2024-02-28 | NT: Same as above, XML Decoding in the Request end to solve the issue, then Table Function for data | Week 8 | XML Decoding Yet to Do then good data from NT, Made PPT for call with Hugo on Friday, worked on previous NT, made Flow Diagram for PPT based on Feedback
2024-02-29 | NT: Same as above, need to find one which works inside the M code itself also, no other scripts | Week 8 | Nothing found wherein I can Decode on the Request side of things as I need to follow a XML Structure inside M Code, or else there is Python and Java ways
2024-03-01 | NT: Same as above, should be solved by the next week for sure, lets do it properly | Week 8 | Had a call with Rajeev, are thinking of a way to solve the issue, call with Hugo and Xiaoming at 8:30 pm, they are fine with the progress so far so working on issue
2024-03-04 | Next would be to Parameterize some Variables which we use as constants and still same NT Man | Week 9 | Had a call with Deepika and Umesh, basically I need to dive into the code and see Tutorials on SOAP XML to properly understand the code issue as all codes mixed can help solve
2024-03-05 | NT: Clean the Table and Join them with headings, then work on Parameters then Movie Data Big 1 GB | Week 9 | Worked on the issue and now am able to get the data onto table form so that is done, now need to work on Parameters and then automate and Join all tables into one table clean way
2024-03-06 | NT: Same as above and see the "Clean" code as that is where we will get all on one Table | Week 9 | Need to look at the Cyclic Problem as that can help solve the Decoding so that each Row does not have any extra data, later try optimizing the code so it can be for any database
2024-03-07 | NT: Now for Movie data, spray using ECL next and see word doc for what graph to make in Power BI | Week 9 | "Clean" solved the issue of Parameters and the Data is now Clean, note the Decoding is done based on a XML Syntax in response. Now to do on Movies data see Word File for steps
2024-03-08 | NT: Sprayed done and see CSV data how will the SOAP Response be and the Word doc for details | Week 9 | Worked on the Spraying but need IP and WSL IP is the one working so I need to Spray via Code and that is working so far, also NT same and see for CSV type data and READ WORD DOC
2024-03-11 | NT: Movies Optimize, CSV data see, Analytics Questions, Fact and Dimension table Star Schema make | Week 10 | Done with Rating now optimize Movies, then we need to see Analytics Questions, CSV file support, make Fact and Dimension Table for DWM schema for unstructure for analytics
2024-03-12 | NT: Rename files in CamelCase, PREVIOUS NT HOLD, SEE GITPOD with viable Use Case in 3 weeks | Week 10 | PREVIOUS TASK ON HOLD FOR NOW, I had a look as a training for Open Source of HPCC Platform, GitPod.yml can config VSC, no ECLIDE web option ? On GitPod then Auth/Local Cluster
2024-03-13 | NT: Same as above, speak to Sathish and Srini and see for overall Architecture and feasibility, Ansible? | Week 10 | Had a look at GitPod's Documentation and say for SSH , Access Token and all, and OIDC which uses Oauth 2.0 for 3rd Party Tool integration, modify the GitPod YAML and CLI
2024-03-14 | NT: Same as above, Xiaoming said send proposal to Hugo, talk to other Managers, see tech way | Week 10 | Had a call with Rajeev and Srini, both seem okay with it, see which team can have a use of such a technology, and pitch it to them, see whole Tech Working and start off with it
2024-03-15 | NT: Same as above, Neeraj will talk to Hugo, if no message continue with the same, and do CLEAN | Week 10 | For next week by Wed or Tue also make sure that you can finish off the ECL work for the large data and also start off with implimentation of GitPod do it fast and nice you got it
2024-03-18 | NT: same as above, see if GitPod VM can have storage, mkdir, use Helm Chart yaml in it's yaml Arya chat | Week 11 | See the NT and also, made the Workspace, took SS, made the Notepad for code for GitPod.yaml, that we need to install Heml so can use charts, do tomorrow then clean before 21st
2024-03-19 | NT: same as above, MAKE PPT FOR HUGO FIRST THING IN THE MORNING, and see GitPod Docs Arya etc | Week 11 | Cleaned the data, names of docs etc then got that data, movie has some issues, on PowerBI , Made some Vizs, that marks the completion of Power BI ,now full focus GitPod
2024-03-20 | NT: Work on GitPod now, as Power BI is done completely, prepare a little for call with Hugo, Same as ab | Week 11 | Finished the PPT needed for Hugo today, showed Rahul the Power BI Integration, Power BI done completely now focus fully on GitPod, and see Arya Chat and mkdir,storage,helm
2024-03-21 | NT: Same as above, see to make POSTER, GITHUB, DOCUMENTATION, YOUTUBE VIDEO, read right side | Week 11 | Had a call with Hugo, need to SHARE CODE of Power BI Integration, make document for it, then proj doc, poster, YT video, github upload, and also each change is DOCKER IMAGE in GitPod
2024-03-22 | NT: Same as above, send the Word Doc to Hugo next week and do DOCS and GitPod | Week 11 | Had made a doc, shown update to Neeraj, wait for that confirmation and then make Poster, PPT, Document, GitHub, and Do GitPod till a decent level to carry on
2024-03-25 | HOLI SO NO WORK DONE | Week 12
2024-03-26 | NT: SAME AS ABOVE AND DOCS AND ALL, SEE NOTEPAD FOR IT, BY WEEKEND DO GITPOD THEN REST | Week 12 | Had a call with Aryaman, firstly by 3rd or Wednesday we need to finish all DOCS, and by this Friday we need to finish off GitPod done with Docker Image, so read it and learn it asap
2024-03-27 | NT: SEE NOTEPAD | Week 12 | Prepare for final week, see gitpod, see if it's possible and make a note for gitpod on your system
2024-03-28 | NT: SAME AS ABOVE | Week 12 | same as above
2024-03-29 | GOOD FRIDAY SO NO WORK DONE | Week 12
2024-04-01 | NT: Same as above, now work on Documentation, code:: and also See for Docs from company and clean | Week 13 | Had a look at the PPTS and made the final PPT for the call on Wednesday, also for college I worked on a Doc which my mentor needed for the week wise break up
2024-04-02 | NT: Same as above | Week 13 | Did the same thing as before, I completed it, mainly I finished the 30 page Technical and Procedural Document, and then the PPT is also done, just what's left is below
2024-04-03 | NT: Poster, Demo Recording, Poster Recording and Experience Letter and Mentor form rev, Mentor Sign | Week 13 | NT: same as above
2024-04-04 | WRAPPING UP WORK | Week 13 | Record Demo Video, make Poster, Record Poster video
2024-04-05 | END | Week 13 | END
END